## Process
Dự án Công nghệ thông tin (Ứng dụng )
Thời gian thực hiện dự án: 08/08/2026 - 21/11/2026 |  | 60 |  |  |  | Today:
2026-09-22
0/122
[10 empty] | Tổng chi tiết hoàn thành | 0
[10 empty] | Tổng chi tiết chưa hoàn thành | 122
[10 empty] | Tổng | 122
#N/A
Giai đoạn | Tuần | Nhiệm vụ | Phân công | Check | Chi tiết | Ghi chú | Theo dõi
Giai đoạn 1 (08/2026): Thực hiện khảo sát các bài báo nghiên cứu khoa học về Agentic RAG | Tuần 33: 11/8 - 17/8 |  | Quân Anh | TRUE | Đọc lướt lần 1 để lọc ra các bài báo |  | 2/2 | 100% | 11.76%
|  |  | Thiên Phúc | TRUE | Thu thập các bài báo
| Tuần 34: 18/8 - 24/8 |  | Thiên Phúc | FALSE | Tiến hành deploy code cho InteRecAgent |  | 0/3 | 0%
|  |  |  | FALSE | Tiến hành deploy code cho AgentCF
FALSE
|  |  | Quân Anh | FALSE
FALSE
FALSE
FALSE
| Tuần 35: 24/8 - 31/8 |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Giai đoạn 2 (09/2025): Xây dựng khung hệ thống Agent và luồng dữ liệu, công việc trong khung hệ thống |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Giai đoạn 3 (10/2026): Xây dựng các công cụ trong khung hệ thống Agent |  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Giai đoạn 4 (11/2026): Thực hiện thí nghiệm và thu thập kết quả |  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE

## Survey Papers
Title | Filter | Year | Conf/Journal | Model | Research Gap | Framework/survey abstract | Dataset | Amazon Dataset Categories | Other Datasets (dropped from H) | Read
Recommendation by Generation - Generation Augmented Complementary Fashion Item Retrieval Using Incomplete Outfit | Type 1 | 2022 |  | RecByGen |  |  | None | None | Polyvore Outfits | None
DRDT Dynamic reflection with divergent thinking for llm-based sequential recommendation | Type 2 single | 2023 |  | DRDT |  |  | MovieLens, Amazon | Video Games, Beauty | None | None
RecMind Large Language Model Powered Agent For Recommendation | Type 2 single | 2023 | Findings of the Association for Computational Linguistics: NAACL 2024 | RecMind (no source code) | Các RS chưa có sự general khi tiếp nhận 1 task recommendation mới hoặc 1 dataset, knowledge mới | Framework Self Inspiring phục vụ cho planning, outperform Chain-of-Thought và Tree-of-Though | Amazon, Yelp | Beauty, Sports, Toys & Games | None | Anh Quân, Thiên Phúc
Retrieval-Augmented Conversational Recommendation with Prompt-Based Semi-Structured Natural Language State Tracking | Evaluation & Benchmark | 2024 | SIGIR 2024 | RA-Rec |  |  | Yelp | None | None | None
A survey on large language models for recommendation | Survey | 2024 |  |  |  |  | None | None | None | None
Large language models for generative recommendation - A survey and visionary discussions | Survey | 2024 | LREC-COLING 2024 |  |  |  | None | None | None | None
Recommender Systems in the Era of Large Language Models (LLMs) | Survey | 2024 | IEEE Transactions on Knowledge and Data Engineering |  |  |  | None | None | None | None
RAH - Recsys–Assistant–Human A Human-Centered Recommendation Framework with LLM Agents | Type 1 | 2024 |  | RAH |  |  | Amazon | Movies, Books, Video Games | None | Anh Quân
CoRAL Collaborative Retrieval-Augmented Large Language Models Improve Long-Tail Recommendation | Type 1 | 2024 | KDD 2024 | CoRAL |  |  | Amazon | Appliances, Gift Cards, Software, Prime Pantry | None | None
Recai Leveraging large language models for next-generation recommender systems | Type 2 single | 2024 | WWW 2024 | RecAI |  |  | None | None | None | None
Large language models are learnable planners for long-term recommendation | Type 2 single | 2024 | SIGIR 2024 | BiLLP | Các framework vẫn có thể bị ảnh hưởng bởi data thưa thớt. | Phương pháp macro-learning và micro-learning. | Steam, Amazon | Books | None | None
Recommender AI - Agent Integrating Large Language Models for Interactive Recommendations | Type 2 single | 2024 | ACM Transactions on Information Systems | InteRecAgent | RecSys truyền thống không thể thực thi những task như giao tiếp với user. Trong khi LLM có thể generic nhưng không có knowledge về sản phẩm. -> Kết hợp cả 2 lại | Có bộ nhớ Memory Bus hoạt động khá giống LSTM (nhưng không phải là LSTM). | Steam, MovieLens, Amazon | Beauty | None | Thiên Phúc, Anh Quân
MACRec A Multi-Agent Collaboration Framework for Recommendation | Type 2 multi | 2024 | SIGIR 2024 | MACRS |  |  | MovieLens, Amazon | None | None | Anh Quân
A Multi-Agent Conversational Recommender System | Type 2 multi | 2024 |  | MACRS |  |  | MovieLens | None | None | None
Let Me Do It For You Towards LLM Empowered Recommendation via Tool Learning | Type 2 single | 2024 | SIGIR 2024 | Tool-Rec |  |  | MovieLens, Amazon, Yelp | Books | Yelp2018 | Anh Quân
AgentCF - Collaborative Learning with Autonomous Language Agents for Recommender Systems | Type 3 (Ignore) | 2024 | WWW 2024 | AgentCF | Các RS chỉ ghi nhận preference của user dựa trên hành động lời nói (tương tác với LLM), chưa có ghi nhận các hành động không qua lời nói như kích chuột vào sản phẩm. Thiếu sự liên kết giữa user-item. | Chia ra 2 agent cho user và item, mỗi lượt tương tác với nhau, sau mỗi lượt reflect để tự điều chỉnh | Amazon | CD & Vinyls, Office Products | None | Anh Quân
CARTS: Collaborative Agents for Recommendation Textual Summarization | Evaluation & Benchmark | 2025 | ICML 2025 | CARTS |  |  | Yelp, Amazon | Books | Google-reviews | Anh Quân
AlignUser Human-Aligned LLM Agents via World Models for Recommender System Evaluation | Evaluation & Benchmark | 2025 |  | AlignUSER |  |  | MovieLens, Steam, Amazon | Books | OPeRA | None
MADREC A Multi-Aspect Driven LLM Agent for Explainable and Adaptive Recommendation | Evaluation & Benchmark | 2025 |  | MADREC |  |  | Amazon | Beauty, Sports, Toys & Games | None | None
RecUserSim A Realistic and Diverse User Simulator for Evaluating Conversational Recommender Systems | Evaluation & Benchmark | 2025 | The Web Conference (WWW) 2025 | RecUserSim |  |  | Yelp | None | Celia Food Assistant | None
Retrieval-Augmented Recommendation Explanation Generation with Hierarchical Aggregation | Evaluation & Benchmark | 2025 |  | REXHA |  |  | Yelp, Amazon | Books | Google-reviews | None
Stealthy LLM-Driven Data Poisoning Attacks against Embedding-Based Retrieval-Augmented Recommender Systems | Evaluation & Benchmark | 2025 | UMAP Adjunct 2025 |  |  |  | MovieLens | None | None | None
A survey on LLM-powered agents for recommender systems | Survey | 2025 | Findings of the Association for Computational Linguistics - EMNLP 2025 |  |  |  | None | None | None | Anh Quân
Recommender systems meet large language model agents - A survey | Survey | 2025 | Foundations and Trends in Privacy and Security |  |  |  | None | None | None | Anh Quân
The Future is Agentic Definitions, Perspectives, and Open Challenges of Multi-Agent Recommender Systems | Survey | 2025 |  |  |  |  | None | None | None | Anh Quân
Towards agentic recommender systems in the era of multimodal large language models | Survey | 2025 |  |  |  |  | None | None | None | Anh Quân
A survey of foundation model-powered recommender systems - From feature-based, generative to agentic paradigms | Survey | 2025 | IEEE Transactions on Knowledge and Data Engineering |  |  |  | None | None | None | None
A survey of large language model empowered agents for recommendation and search - Towards next-generation information retrieval | Survey | 2025 |  |  |  |  | None | None | None | None
AgentCF++ - Memory-Enhanced LLM-Based Agents for Popularity-Aware Cross-Domain Recommendations | Type 1 | 2025 | SIGIR 2025 | AgentCF++ |  |  | Amazon | Books, CD & Vinyls, Movies, Video Games | None | Anh Quân
ItemRAG - Retrieval-Augmented Recommendation with Item-Side Knowledge | Type 1 | 2025 |  | ItemRAG | Các framework vẫn còn yếu trong mảng chuyển hóa lịch sử người dùng sang một lớp ý nghĩa phục vụ cho việc trích xuất gợi ý từ candidate item. -> Biến hóa user-history retrival thô thành item-level retrival đã được tăng cường. Tăng cường hiệu ứng mua kèm sản phẩm dựa trên thông tin ngữ nghĩa. |  | Amazon | Beauty, Toys & Games, Sports, Arts, Crafts & Sewing | None | Anh Quân
Agent0 - Leveraging LLM Agents to Discover Multi-Value Features from Text for Enhanced Recommendations | Type 1 | 2025 | Agent4IR 2025 | Agent0 |  |  | None | None | proprietary production dataset | None
Cloud-Device Collaborative Agents for Sequential Recommendation | Type 1 | 2025 |  | CDA4Rec |  |  | Amazon | Sports | ReDial, Music4All, Foursquare | None
Constraint-Aware Route Recommendation from Natural Language via Hierarchical LLM Agents | Type 1 | 2025 |  | RouteLLM |  |  | None | None | Synthetic grid maps benchmark, OpenStreetMap (Greenwich Village) | None
Intelligent Agents with Adaptive Knowledge Fusion for Personalized Recommendation | Type 1 | 2025 |  | AKF-Agent |  |  | Yelp, GoodReads, Amazon | None | WWW'25 AgentSociety Challenge | None
Large Language Model-Based Recommendation System Agents | Type 1 | 2025 |  | LLMRecAgent |  |  | None | None | None | None
Rethinking Group Recommender Systems in the Era of Generative AI From One-Shot Recommendations to Agentic Group Decision Support | Type 1 | 2025 |  | GRS |  |  | None | None | None | None
The Efficiency vs. Accuracy Trade-off Optimizing RAG-Enhanced LLM Recommender Systems Using Multi-Head Early Exit | Type 1 | 2025 |  | OptiRAG-Rec |  |  | Yelp, Amazon | Beauty, Video Games, Movies | BookCrossing | None
ARAG - Agentic Retrieval Augmented Generation for Personalized Recommendation | Type 2 multi | 2025 |  | ARAG |  |  | Amazon | Books, Clothing, Electronic, Home & Kitchen | None | Anh Quân
iAgent - LLM Agent as a Shield between User and Recommender Systems | Type 1 | 2025 | Findings of the Association for Computational Linguistics - ACL 2025 | Instruct²Rec, InstructAgent | Các recommendation system thuộc e-commercial có thể mang tính bias theo nhu cầu lợi nhuận của các sàn, làm cho tính cá nhân hóa của những người dùng less-active hơn bị giảm đi. -> Tạo ra một lớp trung gian giữa người dùng và rcm sys của e-com. Giữ tính cá nhân hóa cho từng người dùng. |  | Amazon, MovieTV, GoodReads, Yelp | Books | None | Anh Quân
AgenticRAG - Tool-augmented foundation models for zero-shot explainable recommender systems | Type 1 | 2025 |  | AgenticRAG |  |  | Amazon, MovieLens, Yelp | Electronic | None | None
Expectation confirmation preference optimization for multi-turn conversational recommendation agent | Type 1 | 2025 | Findings of the Association for Computational Linguistics - ACL 2025 | ECPO | Các framework khó có thể perform tốt trong các multi-turn dialogue. -> Dựa theo Lý thuyết Xác nhận kỳ vọng (Expectation Confirmation Theory) để optimize. Propose AILO để giả lập feedback người dùng + xác nhận kỳ vọng. |  | Yelp, Amazon | Video Games, Books | None | None
Interactive recommendation agent with active user commands | Type 2 multi | 2025 |  | IRF, RecBot |  |  | MovieLens, Amazon | None | Taobao | None
Smarteats Investigating the effects of customizable conversational agent in dietary recommendations | Type 1 | 2025 | ACM CUI 2025 | SmartEats |  |  | None | None | Online human evaluation experiment (N = 214) | None
Thought-augmented planning for llm-powered interactive recommender agent | Type 2 multi | 2025 |  | TAIRA | Các framework có sự khó khăn trong việc nắm bắt ý định của người dùng trong những query mập mờ, khó hiểu, hoặc không có context. -> Sử dụng phương pháp Chưng cất tư duy để tăng cường agent nắm bắt query của user |  | Amazon | Clothing, Beauty, Music | None | None
Collab-REC - An LLM-based Agentic Framework for Balancing Recommendations in Tourism | Type 2 multi | 2025 |  | Collab-REC |  |  | None | None | SynthTRIPs | None
MAS4POI - A multi-agents collaboration system for next poi recommendation | Type 2 multi | 2025 | PAKDD 2025 | MAS4POI |  |  | None | None | Foursquare-NYC, Foursquare-TKY | None
MATCHA - Can multi-agent collaboration build a trustworthy conversational recommender | Type 2 multi | 2025 | ICML MAS Workshop 2025 | MATCHA |  |  | None | None | OMuleT (Roblox), WildJailbreak | None
MoRE A mixture of reflectors framework for large language model-based sequential recommendation | Type 2 single | 2025 | RecSys 2025 | MoRE |  |  | Amazon | Arts, Crafts & Sewing, Video Games, Musical Instruments | None | None
Re2llm Reflective reinforcement large language model for session-based recommendation | Type 2 single | 2025 | AAAI 2025 | Re2LLM |  |  | MovieLens, Amazon | Video Games | Hetrec2011-Movielens | None
Srlf An agent-driven set-wise reflective learning framework for sequential recommendation | Type 2 single | 2025 | AAAI 2026 | SRLF |  |  | Amazon, MovieLens | CD & Vinyls | None | None
Tunable LLM-based Proactive Recommendation Agent | Type 2 single | 2025 | ACL 2025 | T-PRA |  |  | Steam, Amazon | Books | None | None
Vibemus Proactive agentic system for music personalization | Type 2 single | 2025 | ACM Multimedia Asia (MMAsia) 2025 | VibeMus |  |  | None | None | ToT Music Dataset | None
AgentRecBench Benchmarking LLM Agent-based Personalized Recommender Systems | Type 2 single | 2025 |  | AgentRecBench |  |  | Yelp, GoodReads, Amazon | None | None | Anh Quân
R4ec A reasoning, reflection, and refinement framework for recommendation systems | Type 2 single | 2025 | RecSys 2025 | R4EC |  |  | Amazon, MovieLens | Books | Industrial Dataset | Anh Quân
RuleAgent Discovering Rules for Recommendation Denoising with Autonomous Language Agents | Type 2 single | 2025 |  | RuleAgent |  | Tự động phát hiện quy luật phục vụ cho khử nhiễu hệ thống khuyến nghị ở mức độ tương tác với UI | Amazon, Yelp, Gowalla | Beauty | None | Anh Quân
Large language models empowered personalized web agents | Type 2 single | 2025 | The Web Conference (WWW) 2025 | PUMA |  |  | Amazon | Electronic, Home & Kitchen, Grocery & Gourmet Food, Clothing, Health & Household | PersonalWAB | None
Agentic feedback loop modeling improves recommendation and user simulation | Type 3 (Ignore) | 2025 | SIGIR 2025 | AFL |  |  | Steam, MovieLens | None | Lastfm | None
MAP Multi-User Personalization with Collaborative LLM-Powered Agents | Redundant | 2025 | CHI 2025 | MAP |  |  | None | None | User study logs (n=12) | Thiên Phúc
Get the Agents Drunk Memory Perturbations in Autonomous Agent-based Recommender Systems | Unknown | 2025 |  | DrunkAgent |  |  | Amazon | CD & Vinyls, Office Products, Musical Instruments | None | None
Autonomous Information Seeking A Roadmap for Agentic Recommender Systems | Survey | 2026 |  |  |  |  | None | None | None | None
AdaptJobRec - Enhancing Conversational Career Recommendation through an LLM-Powered Agentic System | Type 1 | 2026 | AAAI 2026 | AdaptJobRec |  |  | None | None | Walmart Job Recommendation System, Walmart associate job transition records, People.AI Knowledge Graph | None
AgentDR Dynamic Recommendation with Implicit Item-Item Relations via LLM-based Agents | Type 2 single | 2026 | The Web Conference (WWW) 2026 | AgentDR |  |  | Instacart, Amazon | Electronic, Sports | None | None
VRAgent-R1 Boosting video recommendation with mllm-based agents via reinforcement learning | Type 1 | 2026 | AAAI 2025 | VRAgent-R1 |  |  | MovieLens | None | MicroLens-100k | None
LLMs as Orchestrators - Constraint-compliant multi-agent optimization for recommendation systems | Type 2 multi | 2026 | WWW 2026 | LLMOrch |  |  | Amazon | Beauty, Electronic, Clothing | None | Anh Quân
Multi-agent collaborative filtering Orchestrating users and items for agentic recommendations | Type 2 multi | 2026 | WWW 2026 | MultiCF |  |  | Amazon | Clothing, Beauty, Music | None | Anh Quân
MemRec Collaborative Memory-Augmented Agentic Recommender System | Type 2 single | 2026 | ACL 2026 | MemRec |  |  | Amazon, GoodReads, MovieTV, Yelp | Books | None | Anh Quân
RAG-VisualRec An Open Resource for Vision-and Text-Enhanced Retrieval-Augmented Generation in Recommendation | Redundant | 2026 | ACM Transactions on Recommender Systems | RAG-VisualRec | Bao gồm Text và Visual. Không trong scope của dự án. |  | MovieLens | None | MMTF-14K | Anh Quân, Thiên Phúc

## ConfereceJournal ranks
Full Name | Abbreviation | Type | CORE Rank
AAAI Conference on Artificial Intelligence | AAAI | Conference | A*
Annual Meeting of the Association for Computational Linguistics | ACL | Conference | A*
ACM Conference on Human Factors in Computing Systems | CHI | Conference | A*
International Conference on Machine Learning | ICML | Conference | A*
ACM SIGKDD Conference on Knowledge Discovery and Data Mining | KDD | Conference | A*
International ACM SIGIR Conference on Research and Development in Information Retrieval | SIGIR | Conference | A*
The Web Conference | WWW | Conference | A*
ACM Conference on Recommender Systems | RecSys | Conference | A
Pacific-Asia Conference on Knowledge Discovery and Data Mining | PAKDD | Conference | A
Joint International Conference on Computational Linguistics, Language Resources and Evaluation | LREC-COLING | Conference | A / C
ACM Conference on User Modeling, Adaptation and Personalization | UMAP (Adjunct) | Conference Track | A (Main conf)
ACM Conference on Conversational User Interfaces | ACM CUI | Conference | Unranked
ACM Multimedia Asia | ACM MMAsia | Conference | Unranked
Findings of the Association for Computational Linguistics | Findings of ACL / EMNLP | Conference Track | N/A
Agent for Information Retrieval Workshop | Agent4IR | Workshop | N/A
ICML Multi-Agent Systems Workshop | ICML MAS | Workshop | N/A
ACM Transactions on Information Systems | ACM TOIS | Journal | N/A
IEEE Transactions on Knowledge and Data Engineering | IEEE TKDE | Journal | N/A
Foundations and Trends in Privacy and Security | FnT Privacy & Sec. | Journal | N/A
Findings of the Association for Computational Linguistics: NAACL 2024 | NAACL | Conference | A
ACM Transactions on Recommender Systems | ACM TORS | Journal | N/A

## Link
Google Drive chứa papers
Annotation/highlight trong Zotero
[Vàng] | Bổ trợ ý chính (cam)
[Cam] | Ý chính của paragraph/paper/framework/section
[Xanh lá] | Đánh dấu dataset/figure/table/citation/reference
[Xanh dương] | Thuật ngữ mới
[Tím] | Đường dẫn code/dataset
[Xám] | Chỗ chưa hiểu
[Đỏ] | Research gap
[Hồng] | So sánh của tác giả so với paper/framework khác
Link dataset
[1] | Yelp | ?
[2] | GoodReads | 2017
[3] | Amazon Review 2023 | 2023
[4] | MovieLens 10M | 2009
[5] | Steam (Review, Metatdata) | 2018
[6] | Tiki | 2023
[7] | face_cleanser | 2023
[8] | RecSysDataset | 2023
[9] | Knowledge-aware Dataset | 2020
Theo dõi trên GitHub
[1] | RUCAIBox
[2] | Amazon Review 2023 | Bao gồm papers Benchmark cho Semantic Presentation, papers Dataset Amazon Review 2023, papers Dataset
[3] | https://recbole.io/model_list.html | Bao gồm model list thuộc RecBole repository