## Process
Dự án Công nghệ thông tin (Ứng dụng )
Thời gian thực hiện dự án: 08/08/2026 - 21/11/2026 |  | 95 |  |  |  | Today:
2026-08-18
0/122
[10 empty] | Tổng chi tiết hoàn thành | 0
[10 empty] | Tổng chi tiết chưa hoàn thành | 122
[10 empty] | Tổng | 122
#N/A
Giai đoạn | Tuần | Nhiệm vụ | Phân công | Check | Chi tiết | Ghi chú | Theo dõi
Giai đoạn 1 (08/2026): Thực hiện khảo sát các bài báo nghiên cứu khoa học về Agentic RAG | Tuần 33: 11/8 - 17/8 |  | Quân Anh | FALSE | Đọc lướt lần 1 để lọc ra các bài báo |  | 0/2 | 0% | 0%
|  |  | Thiên Phúc | FALSE | Thu thập các bài báo được
| Tuần 34: 18/8 - 24/8 |  | Thiên Phúc | FALSE |  |  | 0/3 | 0%
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
| Tuần 35: 24/8 - 31/8 |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Giai đoạn 2 (09/2025): Xây dựng khung hệ thống Agent và luồng dữ liệu, công việc trong khung hệ thống |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Giai đoạn 3 (10/2026): Xây dựng các công cụ trong khung hệ thống Agent |  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Giai đoạn 4 (11/2026): Thực hiện thí nghiệm và thu thập kết quả |  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE
|  |  | Quân Anh | FALSE |  |  | 0/5 | 0% | 0%
FALSE
FALSE
FALSE
FALSE
|  |  | Thiên Phúc | FALSE |  |  | 0/4 | 0%
FALSE
FALSE
FALSE

## Survey Papers
Title | Year | Conf/Journal | Dataset | Model | Abstract | Filter | Read | PDF
Recommendation by Generation - Generation Augmented Complementary Fashion Item Retrieval Using Incomplete Outfit | 2022 |  |  | RecByGen
DRDT Dynamic reflection with divergent thinking for llm-based sequential recommendation | 2023 |  |  | DRDT
RecMind Large Language Model Powered Agent For Recommendation | 2023 |  | Amazon Beauty, Amazon Toys, Amazon Sports, Yelp | RecMind |  | Framework | Anh Quân
A Multi-Agent Conversational Recommender System | 2024 |  |  | MACRS
A survey on large language models for recommendation | 2024
AgentCF - Collaborative Learning with Autonomous Language Agents for Recommender Systems | 2024 | WWW 2024 | Amazon Review | AgentCF |  | Framework | Anh Quân
CoRAL Collaborative Retrieval-Augmented Large Language Models Improve Long-Tail Recommendation | 2024 | KDD 2024 |  | CoRAL
Large language models are learnable planners for long-term recommendation | 2024 | SIGIR 2024 | Steam, Amazon Books | BiLLP |  | Framework
Large language models for generative recommendation - A survey and visionary discussions | 2024 | LREC-COLING 2024
Let Me Do It For You Towards LLM Empowered Recommendation via Tool Learning | 2024 | SIGIR 2024 | Amazon Books, Yelp, ML-1M | Tool-Rec |  | Framework | Anh Quân
MACRec A Multi-Agent Collaboration Framework for Recommendation | 2024 | SIGIR 2024 | None | MACRS |  | Framework | Anh Quân
RAH - Recsys–Assistant–Human A Human-Centered Recommendation Framework with LLM Agents | 2024 |  | Amazon Books, Amazon VIdeo Games, Amazon Movies | RAH |  | Framework | Anh Quân
Recai Leveraging large language models for next-generation recommender systems | 2024 | WWW 2024 |  | RecAI
Recommender AI - Agent Integrating Large Language Models for Interactive Recommendations | 2024 | ACM Transactions on Information Systems | Steam, MovieLens, Amazon Beauty | InteRecAgent |  | Framework | Thiên Phúc, Anh Quân
Recommender Systems in the Era of Large Language Models (LLMs) | 2024 | IEEE Transactions on Knowledge and Data Engineering
Retrieval-Augmented Conversational Recommendation with Prompt-Based Semi-Structured Natural Language State Tracking | 2024 | SIGIR 2024 |  | RA-Rec
A survey of foundation model-powered recommender systems - From feature-based, generative to agentic paradigms | 2025 | IEEE Transactions on Knowledge and Data Engineering
A survey of large language model empowered agents for recommendation and search - Towards next-generation information retrieval | 2025
A survey on LLM-powered agents for recommender systems | 2025 | Findings of the Association for Computational Linguistics - EMNLP 2025 |  |  |  | Survey | Anh Quân
Agent0 - Leveraging LLM Agents to Discover Multi-Value Features from Text for Enhanced Recommendations | 2025 | Agent4IR 2025 |  | Agent0
AgentCF++ - Memory-Enhanced LLM-Based Agents for Popularity-Aware Cross-Domain Recommendations | 2025 | SIGIR 2025 |  | AgentCF++ |  | Framework | Anh Quân
Agentic feedback loop modeling improves recommendation and user simulation | 2025 | SIGIR 2025
AgenticRAG - Tool-augmented foundation models for zero-shot explainable recommender systems | 2025 |  |  | AgenticRAG
AgentRecBench Benchmarking LLM Agent-based Personalized Recommender Systems | 2025 |  |  | AgentRecBench |  | Framework | Anh Quân
AlignUser Human-Aligned LLM Agents via World Models for Recommender System Evaluation | 2025 |  |  | AlignUSER
ARAG - Agentic Retrieval Augmented Generation for Personalized Recommendation | 2025 |  |  | ARAG |  | Framework | Anh Quân
CARTS Collaborative Agents for Recommendation Textual Summarization | 2025 | ICML 2025 |  | CARTS |  | Framework | Anh Quân
Cloud-Device Collaborative Agents for Sequential Recommendation | 2025 |  |  | CDA4Rec
Collab-REC - An LLM-based Agentic Framework for Balancing Recommendations in Tourism | 2025 |  |  | Collab-REC
Constraint-Aware Route Recommendation from Natural Language via Hierarchical LLM Agents | 2025 |  |  | RouteLLM
Expectation confirmation preference optimization for multi-turn conversational recommendation agent | 2025 | Findings of the Association for Computational Linguistics - ACL 2025 |  | ECPO
Get the Agents Drunk Memory Perturbations in Autonomous Agent-based Recommender Systems | 2025 |  |  | DrunkAgent
iAgent - LLM Agent as a Shield between User and Recommender Systems | 2025 | Findings of the Association for Computational Linguistics - ACL 2025 |  | Instruct²Rec, InstructAgent |  | Framework | Anh Quân
Intelligent Agents with Adaptive Knowledge Fusion for Personalized Recommendation | 2025 |  |  | AKF-Agent
Interactive recommendation agent with active user commands | 2025 |  |  | IRF, RecBot
ItemRAG - Retrieval-Augmented Recommendation with Item-Side Knowledge | 2025 |  |  | ItemRAG |  | Framework | Anh Quân
Large Language Model-Based Recommendation System Agents | 2025 |  |  | LLMRecAgent
Large language models empowered personalized web agents | 2025 | The Web Conference (WWW) 2025 |  | PUMA
MADREC A Multi-Aspect Driven LLM Agent for Explainable and Adaptive Recommendation | 2025 |  |  | MADREC
MAP Multi-User Personalization with Collaborative LLM-Powered Agents | 2025 | CHI 2025 |  | MAP
MAS4POI - A multi-agents collaboration system for next poi recommendation | 2025 | PAKDD 2025 |  | MAS4POI
MATCHA - Can multi-agent collaboration build a trustworthy conversational recommender | 2025 | ICML MAS Workshop 2025 |  | MATCHA
MoRE A mixture of reflectors framework for large language model-based sequential recommendation | 2025 | RecSys 2025 |  | MoRE
R4ec A reasoning, reflection, and refinement framework for recommendation systems | 2025 | RecSys 2025 |  | R4EC |  | Framework | Anh Quân
Re2llm Reflective reinforcement large language model for session-based recommendation | 2025 | AAAI 2025 |  | Re2LLM
Recommender systems meet large language model agents - A survey | 2025 | Foundations and Trends in Privacy and Security |  |  |  | Survey | Anh Quân
RecUserSim A Realistic and Diverse User Simulator for Evaluating Conversational Recommender Systems | 2025 | The Web Conference (WWW) 2025 |  | RecUserSim
Rethinking Group Recommender Systems in the Era of Generative AI From One-Shot Recommendations to Agentic Group Decision Support | 2025
Retrieval-Augmented Recommendation Explanation Generation with Hierarchical Aggregation | 2025 |  |  | REXHA
RuleAgent Discovering Rules for Recommendation Denoising with Autonomous Language Agents | 2025 |  |  | RuleAgent |  | Framework | Anh Quân
Smarteats Investigating the effects of customizable conversational agent in dietary recommendations | 2025 | ACM CUI 2025 |  | SmartEats
Srlf An agent-driven set-wise reflective learning framework for sequential recommendation | 2025 | AAAI 2026 |  | SRLF
Stealthy LLM-Driven Data Poisoning Attacks against Embedding-Based Retrieval-Augmented Recommender Systems | 2025 | UMAP Adjunct 2025
The Efficiency vs. Accuracy Trade-off Optimizing RAG-Enhanced LLM Recommender Systems Using Multi-Head Early Exit | 2025 |  |  | OptiRAG-Rec
The Future is Agentic Definitions, Perspectives, and Open Challenges of Multi-Agent Recommender Systems | 2025 |  |  |  |  | Survey | Anh Quân
Thought-augmented planning for llm-powered interactive recommender agent | 2025 |  |  | TAIRA
Towards agentic recommender systems in the era of multimodal large language models | 2025 |  |  |  |  | Survey | Anh Quân
Tunable LLM-based Proactive Recommendation Agent | 2025 | ACL 2025 |  | T-PRA
Vibemus Proactive agentic system for music personalization | 2025 | ACM Multimedia Asia (MMAsia) 2025 |  | VibeMus
AdaptJobRec - Enhancing Conversational Career Recommendation through an LLM-Powered Agentic System | 2026 | AAAI 2026 |  | AdaptJobRec
AgentDR Dynamic Recommendation with Implicit Item-Item Relations via LLM-based Agents | 2026 | The Web Conference (WWW) 2026 |  | AgentDR
Autonomous Information Seeking A Roadmap for Agentic Recommender Systems | 2026
LLMs as Orchestrators - Constraint-compliant multi-agent optimization for recommendation systems | 2026 | WWW 2026 |  | LLMOrch |  | Framework | Anh Quân
MemRec Collaborative Memory-Augmented Agentic Recommender System | 2026 | ACL 2026 |  | MemRec |  | Framework | Anh Quân
Multi-agent collaborative filtering Orchestrating users and items for agentic recommendations | 2026 | WWW 2026 |  | MultiCF |  | Framework | Anh Quân
RAG-VisualRec An Open Resource for Vision-and Text-Enhanced Retrieval-Augmented Generation in Recommendation | 2026 | ACM Transactions on Recommender Systems |  | RAG-VisualRec |  | Framework | Anh Quân
VRAgent-R1 Boosting video recommendation with mllm-based agents via reinforcement learning | 2026 | AAAI 2025 |  | VRAgent-R1
https://drive.google.com/drive/folders/13Rct7N7esgyEsuoeYF9hsRbElAynyVwO?usp=sharing

## ConfereceJournal ranks
Full Name | Abbreviation | Type | CORE Rank
AAAI Conference on Artificial Intelligence | AAAI | Conference | A*
Annual Meeting of the Association for Computational Linguistics | ACL | Conference | A*
ACM Conference on Human Factors in Computing Systems | CHI | Conference | A*
International Conference on Machine Learning | ICML | Conference | A*
ACM SIGKDD Conference on Knowledge Discovery and Data Mining | KDD | Conference | A*
International ACM SIGIR Conference on Research and Development in Information Retrieval | SIGIR | Conference | A*
The Web Conference | WWW | Conference | A*
ACM Conference on Recommender Systems | RecSys | Conference | A
Pacific-Asia Conference on Knowledge Discovery and Data Mining | PAKDD | Conference | A
Joint International Conference on Computational Linguistics, Language Resources and Evaluation | LREC-COLING | Conference | A / C
ACM Conference on User Modeling, Adaptation and Personalization | UMAP (Adjunct) | Conference Track | A (Main conf)
ACM Conference on Conversational User Interfaces | ACM CUI | Conference | Unranked
ACM Multimedia Asia | ACM MMAsia | Conference | Unranked
Findings of the Association for Computational Linguistics | Findings of ACL / EMNLP | Conference Track | N/A
Agent for Information Retrieval Workshop | Agent4IR | Workshop | N/A
ICML Multi-Agent Systems Workshop | ICML MAS | Workshop | N/A
ACM Transactions on Information Systems | ACM TOIS | Journal | N/A
IEEE Transactions on Knowledge and Data Engineering | IEEE TKDE | Journal | N/A
Foundations and Trends in Privacy and Security | FnT Privacy & Sec. | Journal | N/A
ACM Transactions on Recommender Systems | ACM TORS | Journal | N/A